## Plan
number | Task | Task breakdown | Allocated person | Manager actions | deadline | Status
| create new repository |  | Mervin |  | 2024-03-01 | 100%
| lock in BESS size for study |  | Mervin |  | 2024-02-23 | 100%
| Update PSS/E model | Update steady state model/TR/impedances | Mervin |  | 2024-03-04 | 0%
Updated Parameters Mapping Spreadsheet
update dyr files
| Update PSCAD model | Update steady state model/TR/impedances | Mervin |  | 2024-03-04
Updated Parameters Mapping Spreadsheet
update config files
| Update Test spreadsheet |  | Mervin |  | 2024-03-04
| Re-do and update Steady State Study |  | Michael | contact Michael
| RE-run S5.2.5.1 |  | Dao | contact Dao and discuss | 2024-03-06
| Re-run Harmonic Study | estimate how large filter may need to be | Michael
|  | update study and design new filter | Michael
| Run DMAT (Hybrid and BESS) |  | Mervin |  | 2024-03-04
| Benchmarking studies and report (Hybrid and BESS) |  | Mervin |  | 2024-03-04
| Run GPS compliance studies (Hybrid and BESS) and generate Appendix |  |  |  | 2024-03-05
| Connection Study report |  |  |  | 6/03/2024 COB
| VCS |  | Dao | contact Dao | 2024-03-07
| PSDSDS update |  | Dao | contact Dao | 2024-03-07
| GPS update |  | Mervin | Mervin | 2024-03-07

## questions
Number | To | question | Answer
1 | Dao | why scaling of BESS setpoint = 90 MW

## PSSE bus nr equivalence sheet
old nus name | old bus nr | new bus name | new bus nr
SLACK_BUS | 10000 | SLACK_BUS | 10000
2SUMMSF_132A | 273540 | 2HOTS_220A | 334081
2SUMMSF_132B | 273541 | 2HSFBESS_220A | 334090
2SUMMSF_33A | 273530 | 2HSFBESS_33A | 334091
2SUMMSF_33B | 273531 | 2HSFBESS_33B | 334092
2SUMMSF_33C | 273532 | 2HSFBESS_33C | 334093
2SUMMSF_G1 | 273501 | 2HSFBESS_G1 | 334094
2SUMMSF_G2 | 273502 | 2HSFBESS_G2 | 334095